## Sheet1
Project Name | Proxify.gg
Executed By | Vikash Kumar Bharti
Executed Date | 2025-06-03 | BUG REPORT
System | Window 11
Version | 23H2
Bug ID | Description/Summary | Steps to Reproduce | Expected Result | Actual Result | Severity | Priority | Screenshot | FeedBack
BUG-001 | Signup button is not working - Clicking the signup button does not trigger any action, preventing user registration. | 1. Open the signup page 2. Fill in valid signup details 3. Click the "Sign Up" button | User should be registered successfully and receive a confirmation email | Clicking the "Sign Up" button does nothing; no response from the system | Critical | High | BUG URL - https://drive.google.com/file/d/13F_uazsxyM3IMiFotOKugoKZS7-TK9dn/view?usp=sharing | Mention if there are any console errors or network issues when clicking the button.
BUG-002 | Forgot Password button is not available - Users cannot reset their password due to the absence of a "Forgot Password" option. | 1. Navigate to the login page 2. Look for the "Forgot Password" option | "Forgot Password" button should be visible to allow users to reset their password | The "Forgot Password" button is missing from the login page | Major | High | BUG URL - https://drive.google.com/file/d/1RR6x1c5Flg3R3bahbO3iQA9KBh3jAHwP/view?usp=sharing | Specify whether this issue is present only on the login page or if it's missing across all authentication-related pages.
BUG-003 | Password visibility toggle (eye icon) is missing - Users cannot toggle password visibility while entering credentials. | 1. Open the login/signup page 2. Look for the password eye icon next to the password field | Password eye icon should be present to allow users to toggle password visibility | The password eye icon is missing, preventing users from viewing their entered password | Minor | Medium | BUG URL - https://drive.google.com/file/d/1RR6x1c5Flg3R3bahbO3iQA9KBh3jAHwP/view?usp=sharing | Mention whether this issue affects both login and signup or just one of them.
BUG-004 | No error message appears for invalid signup inputs - When users enter invalid data (missing email, weak password), no error message is displayed. | 1. Open the signup page 2. Enter an invalid email user123) 3. Click "Sign Up" | Error message "Enter a valid email address" should appear | No error message is displayed, making it unclear why signup is failing | Major | High |  | List all invalid input cases tested (empty fields, weak passwords, invalid email formats) for better clarity.
BUG-005 | No loading indicator appears on login/signup actions - Users do not see any feedback after clicking login or signup, leading to confusion. | 1. Click "Login" or "Sign Up" 2. Observe the screen while waiting for a response | A loading spinner or progress indicator should appear | No loading indicator is shown, making users think the system is unresponsive | Minor | Low |  | Specify if this happens across both login and signup or only one of them.
BUG-006 | CAPTCHA verification works without entering a password - Users can complete CAPTCHA verification without providing a password, leading to potential security issues. | 1. Open the signup/login page 2. Leave the password field blank 3. Complete the CAPTCHA verification 4. Click "Sign Up" or "Login" | CAPTCHA should not proceed unless all required fields (including password) are filled | CAPTCHA works even when the password field is empty | Major | High | BUG URL - https://drive.google.com/file/d/1PewpVkqCqtL7-nMJC7sP3j5vrwwCIMij/view?usp=sharing | Include if this issue persists even after submission or if CAPTCHA allows proceeding but still fails upon final submission.
BUG-007 | "User Deleted" message appears after entering email and password - When a user enters valid credentials, instead of logging in, the system incorrectly shows a "User Deleted" message. | 1. Open the login page 2. Enter a valid email and password 3. Click the "Login" button | User should be logged in and redirected to the dashboard | "User Deleted" message appears, preventing login | Critical | High | BUG URL - https://drive.google.com/file/d/1DCzR6br_CzdpIV9zD5_tWXYl2qZCkk3-/view?usp=sharing | Confirm whether this issue affects all users or only specific accounts.
BUG-008 | OTP Functionality is Missing | 1. Navigate to https://proxify.gg/login. 2. Enter valid login details (phone number/email). 3. Look for an OTP-based login option. | There should be an OTP-based authentication option for secure login. | There is no OTP functionality available on the login/signup page. | Major | High | BUG URL- https://drive.google.com/file/d/1RR6x1c5Flg3R3bahbO3iQA9KBh3jAHwP/view?usp=sharing | - Security Concern: OTP is a standard security measure for login authentication. - User Experience Impact: Users expecting OTP-based login may face issues.
BUG-009 | Signup with an already registered email does not show a proper error message or allows duplicate accounts | 1. Navigate to the Signup page. 2. Enter an already registered email and fill in other required details. 3. Click the Sign Up button. | The system should display an error message like "This email is already registered. Please log in or use another email." | Either no error message is displayed, or the system allows duplicate registration with the same email. | Major | High |  | The system should properly handle duplicate email registration by displaying a clear error message and preventing duplicate accounts.
BUG-010 | Users are unable to log in again after logging out | 1. Log in with valid credentials. 2. Navigate to the logout option and log out successfully. 3. Try to log in again using the same credentials. | The user should be able to log in again successfully. | The system does not allow the user to log in again after logging out, or an error message appears. | Critical | High |  | The login session should be properly cleared on logout, and users should be able to log in again without any issues.
BUG-011 | "Continue to Payment" button not working | 1. Log in at https://proxify.gg/login with valid credentials. 2. Navigate to https://proxify.gg/dashboard. 3. Click on "Top-up" to go to https://proxify.gg/topup. 4. Click on "Continue to Payment". | User should be redirected to the payment gateway page. | Nothing happens when clicking the button. No redirection, no error message. Console error observed: Uncaught TypeError: Cannot read properties of null (reading 'submit'). | Critical | High | BUG URL- https://drive.google.com/file/d/1e42DDL0TOrcxz3HUA9x79Pq9wlS80QrD/view?usp=sharing | The button does not trigger any response. Check event listener, form submission logic, and JS console errors.